## 1st Iteration
Tasks | Page Category | Priority | Effort in Hours
Rename Today's Agenda to "Pending Visits" and change page scripts accordingly | KAM | 1 | 0.1
Add a visit completion button to "Today's Agenda" + queries + button actions | KAM | 1 | 4
Add storage for images uploaded by KAM visitors | KAM | 1 | 2
Add delete visit option to "Today's Agenda" | KAM | 1 | 2
Make "Today's Agenda" accordian for simple UX and organization | KAM | 1 | 0.2
Show KAM User their own calendar only | KAM | 1 | 1.5
Add a searchable company drop down for KAM user with "Onboarded check" | KAM | 1 | 1
Show pending visits in "Today's Agenda" | KAM | 1 | 2
Add visit remark options when creating a new visit + queries | KAM | 1 | 2.5
Add visited remark options when completing a visit + queries | KAM | 1 | 2.5
Select Visit Type from a dropdown | KAM | 1 | 0.1
Add option and queries for creating a new "potential customer" to visit | KAM | 1 | 1
Add option to upload images to today's agenda | KAM | 2 | 1.5
Make DB changes to track status update, initial start time and visiting date time | KAM | 2 | 3
Add KAM selection option to Leader User + Queries + Support UI elements (with disabling options) | KAM | 2 | 4
Create master view for "Leader User" | Leader | 2 | 2
Write excel queries and export options for ALL the data | Leader | 2 | 4
The summary should show pending visits against visited along with the company names and dates + other useful information | Leader + KAM | 3 | 3.5
Add UI elements to support views like remarks, visited remarks, image, visit type, etc. | Leader + KAM | 3 | 5
41.9

## 2nd Iteration
Tasks | Priority | Effort in Hours
finish Login
finish login validation of js
logout function
make signUp page for user
signup page validation
Signup page Working
make signUp page for content creator
Make Admin view page
Admin's user table
Admin's critic table
Admin's content creator's table
Admin's content list table
Admin can sighnup for critics make that sighnup form
user's landing page
user's profile page
single content page
User's wathclist page
Content creator's profile page
Content creator's content page
Content creator's signup page
Content creator's content list page(will be a table)
Content creator's file upload page
validation for content creator file upload
validation for content creator signup page
Critics landing page will be almost as same as user's one
criticas list from content creators | optional
critics watchlist